## Sheet1
Week 1
Date | Time | Duration(hours) | Activity
2018-07-20 | 12:30 | 2 | Meeting with Supervisor
| Weekly Hours | 2
| Total Hours | 2
Week 2
Date | Time | Duration(hours) | Activity
2018-07-25 | 14:30 - 15:00 | 0.5 | Scrum Meeting with Team
2018-07-27 | 12:30 - 14:30 | 2 | Meeting with Supervisor / Team
2018-07-29 | 16:00 - 18:00 | 2 | Writing Product Backlog List
| Weekly Hours | 4.5
| Total Hours | 6.5
Week 3
Date | Time | Duration(hours) | Activity
2018-07-31 | 15:00 - 18:00 | 3 | Writing Project Charter / Product Backlog List
2018-08-01 | 18:00 - 18:30 | 0.5 | Scrum Meeting
2018-08-02 | 9:30 - 11:20 | 1.75 | Check all documentation, Modifying the documentation, Send email(Project Charter, WBS, PBL) for feedback.
2018-08-05 | 13:00 - 14:00 | 1 | Modifiy project charter based on supervisor feedback and Finialize all documentation
| Weekly Hours | 6.25
| Total Hours | 12.75
Week4
Date | Time | Duration(hours)
2018-08-08 | 14:00 - 16:00 | 2 | Establish the registration Feature
2018-08-08 | 18:00 - 18:30 | 0.5 | Scurm Meeting
2018-08-08 | 18:30 - 20:00 | 1.5 | Continue registration Feature
2018-08-12 | 16:00 - 18:00 | 2 | Modifiying Product Backlog / Trello Board
| Weekly Hours | 6
| Total Hours | 18.75
Week5
2018-08-13 | 17:30 - 18:00 | 0.5 | Create New Use Case Diagram for new topic
2018-08-13 | 18:00 - 19:00 | 1 | Scrum meeting
2018-08-17 | 11:30 - 12:00 | 1 | Preparing the meeting / Finalizing the Use case diagram
2018-08-17 | 12:30 - 14:20 | 2 | Meeting with Sponner
| Weekly Hours | 4.5
| Total Hours | 23.25
Week6
2018-08-22 | 17:00 -18:00 | 1 | Update the PBL and Trello based on new requirment brom Sponser
2018-08-24 | 10:30 - 12:30 | 2 | Create Age validation / Finalize the PBI and Trello
2018-08-25 | 10:30 - 14:10 | 3.75 | devleop registration / Login / encrytion
2018-08-30 | 10:00 - 18:00 | 8
2018-09-01 | 18:00 - 20:00 | 2
| Weekly Hours | 16.75
| Total Hours | 40
Week7
2018-09-04 | 20:00 - 23:00 | 3 | Creating to admin function
2018-09-05 | 10:00 - 17:00 | 7 | Making User Story Card(), Create delete Account, Modify the database Structure
2018-09-06 | 15:30 - 18:30 | 3 | Create change password function
2018-09-07 | 08:30 - 12:30 | 4.5 | Re-finalize (Users and preference) Table / Fix the code based on new timetable
2018-09-07 | 12:30 - 13:00 | 1.5 | Scrum Meeting
2018-09-07 | 14:00 - 17:00 | 3 | Fixed the code issue(Checking reference table when user login )
2018-09-09 | 16:30 - 17:30 | 1 | start to make function(change password)
| Weekly Hours | 23
| Total Hours | 63
Week8
2018-09-10 | 09:00 - 10:45 | 1.75 | complete function (change password)
2018-09-10 | 12:30 - 14:30 | 2 | Matchmaking Algorithm start
2018-09-10 | 18:30 - 22:30 | 4 | Matchmaking Algorithm (Pending)
2018-09-12 | 15: 00 - 17:00 | 2 | Modify the preference Page based on Matchmaking Algorithm(Start)
2018-09-12 | 18:00 - 18:30 | 0.5 | Scrum Meeting
2018-09-12 | 20:00 - 24:00 | 4 | Modify the preference Page based on Matchmaking Algorithm(Continue)
2018-09-13 | 11:00 - 13:00 | 2 | Modify the preference Page based on Matchmaking Algorithm(Continue)
2018-09-13 | 20:40 - 21:40 | 1 | Modify the preference Page based on Matchmaking Algorithm(Continue)
2018-09-13 | 22:00 - 23:20 | 1.66 | Modify the preference Page based on Matchmaking Algorithm(Continue)
2018-09-14 | 09:30 - 12:10 | 2.66 | Modify the preference Page based on Matchmaking Algorithm(Continue) -- Age, Gender, Location Only (done)
2018-09-14 | 12:30 - 14:30 | 2 | Scrum Meeting
| Weekly Hours | 23.57
| Total Hours | 86.57
Week9
2018-09-19 | 15:00 - 17:00 | 2 | Logout function(done)
2018-09-19 | 18:00 - 18:20 | 0.33 | Scrum online Meeting
2018-09-21 | 12:30 - 14:30 | 2 | Scrum Meeting
| Weekly Hours | 4.33
| Total Hours | 90.9
Week10
2018-09-23 | 16:00 - 21:00 | 3 | Edit User information function (progress)
2018-09-24 | 18:00 - 18:30 | 0.5 | Online Scrum Meeting
| Weekly Hours | 3.5
| Total Hours | 94.4
Week11
04/10/2018 - 05/10/2018 | 23:00: - 03:00 | 4 | Complete the change personal information (done) / Age verification (in progress)
2018-10-05 | 08:00 - 11:30 | 4 | Age verification(done) // Docuemtation
2018-10-05 | 12:30 - 1:30 | 2 | Scrum Meeting
| Weekly Hours | 10
| Total Hours | 104.4
Week12
2018-10-08 | 14:00 - 15:30 | 2.5 | Finialzie User stories and Product Backlog Item list documentation
2018-10-08 | 18:00 - 01:00 | 7 | Finialzie User stories and Product Backlog Item list documentation / Matching User display / Algoritm modify
2018-10-09 | 09:30 - 10:30 | 1 | Wrting the Learning Outcomes Documentation
2018-10-10 | 18:00 - 19:30 | 1.5 | Scrum online Meeting / Quality Assureance (Index Page, The person who likes you page, Profile Picture)
2018-10-11 | 10:00 - 12:30 | 2.5 | sending result from person_who_likes_me page to My Match page(done)
2018-10-12 | 08:30 - 12:30 | 4 | Admin view history modify / user report(In progress) / disconnect message function (done)
2018-10-14 | 13:00 - 25:00 | 12 | Code integration / documentation merge
| Weekly Hours | 30.5
| Total Hours | 134.9
Week14
2018-10-30 | 13:00 - 16:00 | 3 | PRR
2018-11-01 | 12:00 - 19:40 | 7.66 | Validation & Testing (password change, Login, My_message, recommendation )
2018-11-02 | 11:00: - 18:00 | 7 | Validation & Testing (person who likes me page, edit_preference, edit_information ), Edit user story card,
2018-11-03 | 11:00 - 17:00 | 6 | Edit user story card, Validation & Testing (Report user, Admin delete Account, View_profile)
2018-11-04 | 00:00 - 03:00 | 3 | Edit user story Card, Validation & Testing (Whole Admin functionaility)
2018-11-04 | 08:30 : 9:50 | 1.33 | Edit user story Card, Validation & Testing (Whole Admin functionaility)
| Weekly Hours | 27.99
| Total Hours | 162.89