## Sheet1
Week1
Date | Time In | Time Out | Duration (Hours) | Activity
2018-07-20 | 12:30 | 14:30 | 2 | Meeting with the supervisor, form a project group, document meeting minutes.
|  | Total hours | 2
Week2
Date | Time In | Time Out | Duration (Hours) | Activity
2018-07-25 | 14:30 | 15:00 | 0.5 | Scrum meeting with the team, document meeting minutes.
2018-07-27 | 12:30 | 14:30 | 2 | Meeting with client / team discussion, document meeting minutes.
|  | Total hours | 2.5
Week3
Date | Time In | Time Out | Duration (Hours) | Activity
2018-07-31 | 16:00 | 17:10 | 2.2 | Working on project charter documentation
| 19:20 | 20:20 | 1 | Working on project charter documentation and set up C9 enviroment for the team
2018-08-01 | 18:00 | 18:30 | 0.5 | Having a team online scrum meeting via Slack. Discuss task progress and any team issues.
Document meeting minutes.
2018-08-03 | 12:30 | 14:30 | 2 | Having an in-class meeting with team and supervisor to discuss current progress of project.
Document meeting minutes.
| 15:00 | 16:00 | 1 | Update project charter, document meeting minutes.
|  | Total hours | 6.7
Week4
Date | Time In | Time Out | Duration (Hours) | Activity
2018-08-08 | 18:00 | 18:20 | 0.3 | Having a team online scrum meeting via Slack. Discuss task progress and any team issues.
2018-08-10 | 0:00 | 0:30 | 0.5 | Creating a wireframe for sprint1.
2018-08-10 | 2:00 | 2:10 | 0.2 | Setting up new AWS cloud9 workspace for the group members.
2018-08-10 | 12:30 | 14:30 | 2 | Having an in class team meeting, decided to change new project topic (Dating website).
2018-08-10 | 11:40 | 11:50 | 0.2 | Documented in class team meeting minutes.
|  | Total hours | 3.2
Week5
Date | Time In | Time Out | Duration (Hours) | Activity
2018-08-13 | 18:00 | 19:00 | 1 | Having an online scrum meeting via Slack. Dicussed about feedback, new project requirements.
2018-08-13 | 19:00 | 19:20 | 0.3 | Documented online scrum team meeting minutes.
2018-08-16 | 21:00 | 22:00 | 1 | Set up a new project workspace, created an index page (login, register form)
2018-08-16 | 22:00 | 22:30 | 0.5 | Created a spint2 wireframe
2018-08-17 | 12:30 | 14:30 | 2 | Having an inclass meeting with the client, share ideas with the team, divide the task for each member.
2018-08-17 | 14:30 | 14:50 | 0.3 | Documented team meeting minutes.
|  | Total hours | 5.1
Week6
Date | Time In | Time Out | Duration (Hours) | Activity
2018-08-21 | 23:40 | 12:50 | 1.2 | Added 'Age' input in the user register form, display age info in user account after login.
2018-08-22 | 18:00 | 18:30 | 0.5 | Having an online scrum meeting via Slack. Discuss each member's task progress and any obstacles.
2018-08-22 | 19:00 | 19:20 | 0.3 | Documented online scrum team meeting minutes.
2018-08-23 | 20:00 | 20:10 | 0.2 | Created a wireframe for sprint3
2018-08-24 | 12:30 | 14:30 | 2 | In class meeting with client, get a feedback, devide a task for next sprint.
2018-08-25 | 13:40 | 15:40 | 2 | created user preferences form,set up and fixed db issue (post data to database).
2018-08-26 | 0:00 | 0:30 | 0.5 | fixed layout of preference form
|  | Total hours | 6.4
Mid-break
Date | Time In | Time Out | Duration (Hours) | Activity
2018-08-28 | 1:00 | 2:20 | 1.4 | Finished user preference form, created wireframe for sprint4
2018-08-30 | 19:00 | 20:30 | 1.5 | Fix login, registration form (client side and server side), Edit database table.
2018-08-31 | 0:30 | 2:00 | 1.5 | Fix errors (data not inserted) in preference form, recreated preference table in database.
2018-08-31 | 18:00 | 19:40 | 1.6 | Having online scrum meeting, discussed progress and team issues.
2018-08-31 | 20:00 | 20:20 | 0.3 | Documented online scrum team meeting minutes.
2018-09-01 | 9:50 | 10:50 | 1 | Created admin login page, only admin can login to admin panel other users can't login to admin page.
2018-09-02 | 23:20 | 23:50 | 0.5 | Created admin panel layouts
2018-09-03 | 0:30 | 0:50 | 0.4 | Fixed admin panel layouts
|  | Total hours | 8.2
Week7
Date | Time In | Time Out | Duration (Hours) | Activity
2018-09-05 | 18:00 | 18:30 | 0.5 | Having online scrum meeting, discussed progress and team issues.
2018-09-05 | 18:30 | 18:40 | 0.2 | Documented online scrum team meeting minutes.
2018-09-06 | 3:00 | 3:30 | 0.5 | Created a wireframe for sprint5
2018-09-07 | 12:30 | 2:30 | 2 | In class meeting with client, disuss team issues, get a feedback, devide a task for next sprint.
2018-09-08 | 10:40 | 12:00 | 1.3 | Read user information from db (only current logged in user), display it on dashboard.
|  | Total hours | 4.5
Week8
Date | Time In | Time Out | Duration (Hours) | Activity
2018-09-11 | 12:30 | 14:30 | 2 | Worked on retrieve matched user data using next button, for loop, currently only load 1 row.
2018-09-11 | 15:00 | 16:50 | 1.8 | Worked on retrieve matched user data using php pagination, still need to work.
2018-09-11 | 20:50 | 21:30 | 0.6 | Matched preference user data showed using php pagination. (done)
2018-09-12 | 16:35 | 17:05 | 0.5 | Create a wireframe for sprint6
2018-09-12 | 18:00 | 18:20 | 0.3 | Having online scrum meeting, discussed progress.
2018-09-14 | 12:30 | 14:30 | 2 | Having an in class meeting with team and client, discuss the task progress and get a feedback.
|  | Total hours | 7.2
Week9
Date | Time In | Time Out | Duration (Hours) | Activity
2018-09-17 | 16:00 | 17:15 | 1.3 | put logo & make logo as link (go to index) in registration page
add interest1, interest2, remove habit from user table, edited sql query for match user (age, city, gender)
2018-09-18 | 21:05 | 22:40 | 1.5 | edit user preference form & db table, edit pagination function in registation page. (add previous and next)
2018-09-19 | 16:00 | 16:30 | 0.5 | create a wireframe for sprint7
2018-09-19 | 18:00 | 18:20 | 0.3 | Having online scrum meeting, discussed progress.
2018-09-20 | 16:40 | 18:00 | 1.4 | edit registration&preference form, added dumping data in user table for testing
2018-09-20 | 19:30 | 21:20 | 1.8 | worked on algorithm phase2 (sql query)
2018-09-21 | 12:30 | 14:30 | 2 | In class team meeting with the client, discuss team progress and preperation for wk12 & final submission.
|  | Total hours | 8.8
Week10
Date | Time In | Time Out | Duration (Hours) | Activity
2018-09-25 | 23:40 | 0:05 | 0.4 | Created a wireframe for sprint8, delete 'send message btn' in recomendation page and move it to match.
2018-09-26 | 0:20 | 0:40 | 0.2 | Fix pagination function. Next button doesn't show and work when it reaches to the last result set.
2018-09-26 | 18:00 | 18:30 | 0.5 | Online scrum meeting with team, discuss task progress and issues.
|  | Total hours | 1.1
Week11
Date | Time In | Time Out | Duration (Hours) | Activity
2018-10-01 | 18:00 | 18:30 | 0.5 | Online scrum meeting with team, discuss task progress and issues.
2018-10-04 | 18:50 | 19:30 | 0.6 | Created a wireframe for sprint 9.
2018-10-04 | 19:40 | 21:20 | 1.6 | create user_likes table, user id updated to db table if user click like button.
2018-10-04 | 22:00 | 23:20 | 1.4 | Trying to retreive liked user id but was not working.
2018-10-05 | 12:30 | 14:30 | 2 | In class team meeting with the client, discuss team progress and preperation for draft submission.
|  | Total hours | 6.1
Week12
Date | Time In | Time Out | Duration (Hours) | Activity
2018-10-08 | 16:30 | 17:00 | 0.5 | Worked on draft submission documentation.
2018-10-08 | 20:50 | 22:20 | 1.5 | Change user_likes db table, change match.php page to retrieve user information, add pagination.
2018-10-08 | 23:00 | 23:20 | 0.4 | worked on draft submission documentation.
2018-10-08 | 23:50 | 1:50 | 2 | fetch user result array using mysql in match.php , apply pagination.
2018-10-09 | 20:10 | 21:40 | 1.5 | worked on draft submission documentation. (learning outcomes) done.
2018-10-10 | 1:10 | 1:40 | 0.5 | worked on draft submission documentation. (OWASP document)
2018-10-10 | 16:20 | 17:20 | 1 | Finish OWASP document.
2018-10-10 | 18:00 | 18:30 | 0.5 | Having an online scrum meeting with team, discuss task progress
2018-10-10 | 22:10 | 23:40 | 1.5 | remove pagination number list in recommendation page, user can see next result with pass button instead.
2018-10-11 | 0:50 | 1:25 | 0.6 | created a wireframe for sprint10 (final wifreframe)
2018-10-12 | 0:30 | 2:00 | 1.5 | retrieve matched user data array table in send_message page. All matched user shown in one page.
2018-10-12 | 12:30 | 14:30 | 2 | In class team meeting with the client, discuss team progress and preperation for draft submission.
2018-10-13 | 15:10 | 15:50 | 0.6 | worked on draft submission documentation. (team document and learning outcomes)
2018-10-14 | 17:20 | 17:50 | 0.5 | Merge two filters queries into one query to retreive the dataset.
|  | Total hours | 14.6
Week13
Date | Time In | Time Out | Duration (Hours) | Activity
2018-10-17 | 2:00 | 3:00 | 1 | Added user profile images into db tables for testing, retrieve user profile image instead of static image.
2018-10-17 | 18:00 | 18:30 | 0.5 | Online scrum meeting with team, discuss task progress and any issues.
2018-10-20 | 20:00 | 21:40 | 1.6 | Updated user manual
2018-10-20 | 21:40 | 22:00 | 0.4 | Updated project charter (amendement history)
2018-10-20 | 22:50 | 0:10 | 1.5 | Updated techncical solution design document.
|  | Total hours | 5
Week14
Date | Time In | Time Out | Duration (Hours) | Activity
2018-10-26 | 17:40 | 21:10 | 3.5 | Created UI performance document.
2018-10-27 | 23:50 | 1:30 | 1.6 | Created a peer reviewed report.
|  | Total hours | 5.1
Week15
Date | Time In | Time Out | Duration (Hours) | Activity
2018-11-03 | 15:00 | 16:00 | 1 | Update pagination feature in matching.php page
|  | Total hours | 1
|  | Total hours (all) | 87.5